## Slide 1
Aladdin
6-week delivery plan
1.5 months · 5 phases · 15,000 products
5 h
per day on Aladdin
3 h
per day on Talents
150 h
Aladdin capacity in 6 weeks
The 3 daily hours for Talents cover tickets and problems, supervising tech logic and profiles, updates, and risk.

## Slide 2: Five phases for Aladdin
# | Phase | What it includes | Effort | When
1 | New palette and logo on the landing page | Apply the 2026 brand colors and logo to the landing page | 16 h | W2–W3
2 | Add the marketplace | List, filters and product details on real data; landing section; release flag | 28 h | W3–W5
3 | Schema and database for products | Dynamic product schema, catalog, variants, stock, security, tests | 40 h | W1–W2
4 | BestTrade as a showroom account | Create the account through the existing flow and enable it as the first seller | 8 h | W2
5 | Upload 15,000 products | Import tool, image pipeline, batch load and exception handling | 46 h | W3–W5
 | Planned total | of 150 h capacity; the remaining 12 h absorb slippage | 138 h | W1–W6

## Slide 3: Timeline: 6 weeks
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
3 Schema and database for products
4 BestTrade showroom account
1 Apply the new palette on landing
5a Import tool
5b Image pipeline
5c Load 15,000 and exceptions
2 Marketplace on real data
Stabilize, test, demo, handover
Week 6 is reserved for stabilization and any slippage; the plan has about 12 h of slack across the other weeks.

## Slide 4: Daily split: 5 h Aladdin, 3 h Talents
Chart: Hours per working day
| Each day
Aladdin (5 h) | 5
Talents (3 h) | 3
Aladdin: 5 h/day
150 h over 6 weeks (30 working days). 138 h planned, 12 h slack.
Talents: 3 h/day
Tickets and problems, supervising tech logic and profiles, updates, and risk.
Protected hours
Talents hours are not used for Aladdin scope; unused ones speed up delivery.

## Slide 5: What is needed to hold the timeline
1
A second Claude account
To work on both projects in parallel when a Talents ticket and an Aladdin task collide, so the timeframe is not broken.
2
Data sample
20–30 real product rows, and whether the 15,000 are products or sellable items.
3
Images
Location, naming and size of the product images, and who provides them.